## Lead Database
Lead ID | Full Name | Salon Name | City | State | Platform Found | Instagram Handle | Email | Phone | Website | Follower Count | Running Ads? | Lead Score | Lead Tier | Current Phase | First Contact Date | First Contact Channel | First Response Date | Response Status | Follow-Up Count | Last Follow-Up Date | Landing Page Click? | Purchased? | Purchase Date | Notes
L001 | Maria Rodriguez | Glow Beauty Salon | Miami | FL | Instagram | @glowbeautymiami | maria@glowbeauty.com | 305-555-0123 | glowbeautysalon.com | 3200 | Yes | 75 | HOT | Attention | 2026-04-01 | Instagram DM | 2026-04-02 | Replied - Interested | 2 | 2026-04-05 | Yes | No |  | Very interested, asked about reactivation module
L002 | Jennifer Kim | JK Hair Studio | Los Angeles | CA | Apollo.io | @jkhairstudio | jen@jkhairstudio.com | 310-555-0456 | jkhairstudio.com | 5600 | Yes | 55 | WARM | Interest | 2026-04-01 | Cold Email | 2026-04-04 | Replied - Maybe | 1 | 2026-04-04 | No | No |  | Opened email 1 and 2, replied asking for more info
L003 | Tasha Williams | Crown & Glory | Atlanta | GA | Facebook Group | @crownandgloryatl | tasha@crownandglory.com | 404-555-0789 | crownandglorysalon.com | 1800 | Unknown | 35 | COOL | Attention | 2026-04-03 | Facebook DM |  | No Response | 1 | 2026-04-07 | No | No |  | Engaged with FB group post but no DM reply
L004 | Fatima Hassan | Luxe Locks Salon | Houston | TX | Google Maps | @luxelockshtx | fatima@luxelocks.com | 713-555-0321 | luxelockssalon.com | 7800 | Yes | 85 | HOT | Desire | 2026-04-01 | Instagram DM | 2026-04-01 | Clicked Link | 3 | 2026-04-10 | Yes | No |  | Clicked link twice, sent WhatsApp voice note
L005 | David Chen | Studio 88 Hair | San Francisco | CA | LinkedIn |  | david@studio88hair.com | 415-555-0654 | studio88hair.com | 2100 | No | 25 | COOL | Attention | 2026-04-05 | LinkedIn |  | No Response | 0 |  | No | No |  | Connected on LinkedIn, no reply to message

## Daily Activity Log
Date | Day | Week # | Phase | IG DMs Sent | IG DM Replies | DM Reply Rate | Emails Sent (GHL) | Email Opens | Email Open Rate | Email Replies | Email Click-Throughs | LinkedIn Requests | LinkedIn Accepted | LinkedIn Messages | LinkedIn Replies | FB Group Comments | FB Group Posts | WhatsApp Sent | WhatsApp Replies | Landing Page Visits | Sales | Revenue | Notes
2026-04-06 | Monday | 1 | Attention
2026-04-07 | Tuesday | 1 | Attention
2026-04-08 | Wednesday | 1 | Attention
2026-04-09 | Thursday | 1 | Attention
2026-04-10 | Friday | 1 | Attention
2026-04-11 | Saturday | 1 | Attention
2026-04-12 | Sunday | 1 | Attention
2026-04-13 | Monday | 2 | Attention
2026-04-14 | Tuesday | 2 | Attention
2026-04-15 | Wednesday | 2 | Attention
2026-04-16 | Thursday | 2 | Attention
2026-04-17 | Friday | 2 | Attention
2026-04-18 | Saturday | 2 | Attention
2026-04-19 | Sunday | 2 | Attention
2026-04-20 | Monday | 3 | Interest
2026-04-21 | Tuesday | 3 | Interest
2026-04-22 | Wednesday | 3 | Interest
2026-04-23 | Thursday | 3 | Interest
2026-04-24 | Friday | 3 | Interest
2026-04-25 | Saturday | 3 | Interest
2026-04-26 | Sunday | 3 | Interest
2026-04-27 | Monday | 4 | Interest
2026-04-28 | Tuesday | 4 | Interest
2026-04-29 | Wednesday | 4 | Interest
2026-04-30 | Thursday | 4 | Interest
2026-05-01 | Friday | 4 | Interest
2026-05-02 | Saturday | 4 | Interest
2026-05-03 | Sunday | 4 | Interest
2026-05-04 | Monday | 5 | Desire
2026-05-05 | Tuesday | 5 | Desire
2026-05-06 | Wednesday | 5 | Desire
2026-05-07 | Thursday | 5 | Desire
2026-05-08 | Friday | 5 | Desire
2026-05-09 | Saturday | 5 | Desire
2026-05-10 | Sunday | 5 | Desire
2026-05-11 | Monday | 6 | Action
2026-05-12 | Tuesday | 6 | Action
2026-05-13 | Wednesday | 6 | Action
2026-05-14 | Thursday | 6 | Action
2026-05-15 | Friday | 6 | Action
2026-05-16 | Saturday | 6 | Action
2026-05-17 | Sunday | 6 | Action
TOTALS

## Weekly Dashboard
Week # | Phase | Total DMs Sent | Total DM Replies | DM Reply Rate | Total Emails Sent | Total Email Opens | Email Open Rate | Total LinkedIn Outreach | LinkedIn Accept Rate | Total LP Visits | Total Sales | Total Revenue | Conversion Rate | Notes
1 | Attention
2 | Attention
3 | Interest
4 | Interest
5 | Desire
6 | Action
GRAND TOTAL

## Email Sequence Tracker
Email # | Email Name | Phase | Subject Line A | Subject Line B | Send Date | Total Sent | Opens (A) | Open Rate (A) | Opens (B) | Open Rate (B) | Winner | Total Clicks | CTR | Unsubscribes | Replies | Sales Attributed | Notes
1 | The Pain | Interest | Are you renting clients or building a business? | The $48,000 mistake most salon owners make every year
2 | Social Proof | Interest | 23 clients came back. Zero ad spend. | How Fatima stopped paying $4,000/month for ads
3 | The Tease | Interest | The 8-module system that filled 500+ salon calendars | Before I show you the price — here's what's inside
4 | Offer Reveal | Desire | Here's everything you get — and the price drops today | $1,041 in value. $97 today.
5 | Bonus Stack | Desire | Here's what you lose if you wait | The bonuses disappear before the price goes up
6 | Testimonials | Desire | Real salon owners. Real numbers. | From $4,000/month in ads to $0 — their stories
7 | 48hr Warning | Action | 48 hours left — then the price goes back to $497 | The math on waiting vs. enrolling right now
8 | 24hr Warning | Action | Last chance — 24 hours before the price changes | What if it doesn't work? (Read this guarantee)
9 | Final Close | Action | This is it — closing in 6 hours [FINAL NOTICE] | Final email. Then it's done.

## Channel Performance
Channel | Total Outreach | Total Responses | Response Rate | LP Clicks | Click Rate | Sales | Conversion Rate | Revenue | Time (hrs) | Revenue/Hour | Priority | Notes
Instagram DM
Cold Email (GHL)
LinkedIn
Facebook Groups
WhatsApp
Threads
TOTAL

## 6-Week Execution Calendar
Date | Day | Week # | Phase | Morning (9-11 AM) | Midday (11 AM-1 PM) | Afternoon (2-4 PM) | Evening (4-6 PM) | Key Deliverable | Status
2026-04-06 | Monday | 1 | Attention | Set up GHL sub-account, configure pipeline stages and tags | Set up Apollo.io, save search filters, start building email list | Join 8 Facebook groups, optimize Instagram bio + link | Prepare first 3 Instagram DM script variants | All platforms set up and configured | Not Started
2026-04-07 | Tuesday | 1 | Attention | Warm email domain (start process), install G Maps Extractor | Scrape first 2 cities: Miami + LA (Google Maps) | Start Apollo.io list build (target: 200 contacts today) | Verify scraped data, clean email list | 200+ leads scraped and verified | Not Started
2026-04-08 | Wednesday | 1 | Attention | Send first batch of Instagram DMs (30 DMs) | Continue Apollo.io list build (target: 300 more) | Scrape 2 more cities: Houston + NYC | Comment on 5+ posts in Facebook groups | 30 DMs sent, 500 leads total | Not Started
2026-04-09 | Thursday | 1 | Attention | Instagram DMs (40 DMs), track responses | Load first email batch into GHL (do NOT send yet) | Scrape 2 more cities: Chicago + Dallas | Continue Facebook group commenting | 40 DMs sent, 700+ leads | Not Started
2026-04-10 | Friday | 1 | Attention | Instagram DMs (50 DMs), review reply rate | Finalize email list in GHL (500+ contacts) | Scrape 2 more cities: Atlanta + Tampa | Review Week 1 progress, adjust scripts if needed | 50 DMs sent, 1000+ leads in database | Not Started
2026-04-11 | Saturday | 1 | Attention | Light DM follow-ups to replies | Organize and clean all lead data | Content planning for next week | Rest / review metrics | Database organized | Not Started
2026-04-12 | Sunday | 1 | Attention | Plan Week 2 priorities | Review DM reply rate and best-performing opener | Prep email sequences in GHL for Week 2 launch | Rest | Week 2 plan ready | Not Started
2026-04-13 | Monday | 2 | Attention | Instagram DMs (50/day), A/B test openers | Launch first cold email batch in GHL (150/day) | Start LinkedIn outreach (20 requests/day) | First organic Facebook group post | Email + DM + LinkedIn all active | Not Started
2026-04-14 | Tuesday | 2 | Attention | Instagram DMs (50/day), track responses | Monitor email open rates, adjust subject lines | LinkedIn connection follow-ups | Facebook group commenting | All channels running | Not Started
2026-04-15 | Wednesday | 2 | Attention | Instagram DMs (40/day) + reply to responses | Cold emails (150/day), review A/B results | LinkedIn messages to new connections | Second Facebook group post | Mid-week metric review | Not Started
2026-04-16 | Thursday | 2 | Attention | Instagram DMs (40/day) | Cold emails (200/day) — double down on winning subject line | LinkedIn outreach (25/day) | Facebook group commenting + engagement | 200+ emails/day milestone | Not Started
2026-04-17 | Friday | 2 | Attention | Instagram DMs (40/day) + nurture warm leads | Review email metrics: opens, clicks, replies | LinkedIn (20/day) | WEEKLY REVIEW: DM rate, email rate, LP visits | Weekly KPI review complete | Not Started
2026-04-18 | Saturday | 2 | Attention | Light follow-ups only | Prep Phase 2 (Interest) materials | Organize warm leads list | Content review | Warm leads identified | Not Started
2026-04-19 | Sunday | 2 | Attention | Plan Phase 2 transition | Review and segment leads by tier | Prep nurture sequences | Rest | Phase 2 plan ready | Not Started
2026-04-20 | Monday | 3 | Interest | Launch Email Sequence 1-3 in GHL (nurture phase) | Instagram DMs (25/day) — nurture warm leads | Start Instagram 5-day story series (Day 1: RANK) | LinkedIn posts 2x this week | Nurture emails live | Not Started
2026-04-21 | Tuesday | 3 | Interest | Instagram Story Day 2: CONVERT | DMs (25/day) — value-add messages to warm leads | Monitor email opens/clicks on Email 1 | Facebook group post + engagement | Story series running | Not Started
2026-04-22 | Wednesday | 3 | Interest | Instagram Story Day 3: REACTIVATE | DMs (20/day) — follow up with story viewers | LinkedIn post #1 this week | Review Email 1 performance | Mid-week nurture check | Not Started
2026-04-23 | Thursday | 3 | Interest | Instagram Story Day 4: REFER | DMs (20/day) | Monitor Email 2 performance | Facebook group commenting | Nurture progressing | Not Started
2026-04-24 | Friday | 3 | Interest | Instagram Story Day 5: SYSTEM OVERVIEW | DMs (20/day) | WEEKLY REVIEW: warm lead count, email engagement | Prepare Phase 3 materials if warm leads > 50 | Weekly review + Phase 3 prep | Not Started
2026-04-25 | Saturday | 3 | Interest | Light follow-ups | Review story engagement metrics | Segment leads: who engaged most? | Rest | Lead segments updated | Not Started
2026-04-26 | Sunday | 3 | Interest | Plan Week 4 priorities | Review warm vs cold lead ratios | Adjust strategy if warm leads < 50 | Rest | Week 4 plan ready | Not Started
2026-04-27 | Monday | 4 | Interest | Continue nurture DMs (20/day) — value content | Monitor Email 3 performance in GHL | LinkedIn post + engagement | Facebook group post | Nurture continues | Not Started
2026-04-28 | Tuesday | 4 | Interest | DMs (20/day) — check-in messages | Prep Email 4-6 (Desire phase) in GHL | LinkedIn connection follow-ups | Engage with warm leads on their posts | Desire emails prepped | Not Started
2026-04-29 | Wednesday | 4 | Interest | DMs (20/day) — share success stories | Review all email metrics so far | LinkedIn engagement | Facebook group commenting | Email metrics reviewed | Not Started
2026-04-30 | Thursday | 4 | Interest | DMs (15/day) — focus on warm leads only | CRITICAL: Count warm leads. If < 50, add more cold outreach | Prep WhatsApp Business account | Plan live elements for Phase 3 | Warm lead count assessed | Not Started
2026-05-01 | Friday | 4 | Interest | DMs (15/day) | WEEKLY REVIEW: total warm leads, engagement rates | Finalize Phase 3 launch plan | Prepare urgency messaging | Phase 3 launch plan finalized | Not Started
2026-05-02 | Saturday | 4 | Interest | Light follow-ups | Organize all warm leads for Phase 3 push | Test all Phase 3 emails | Rest | Phase 3 ready to launch | Not Started
2026-05-03 | Sunday | 4 | Interest | Final Phase 3 prep | Review all scripts and messaging | Mental prep for push week | Rest | Ready for Phase 3 | Not Started
2026-05-04 | Monday | 5 | Desire | Launch Email 4 (Offer Reveal) in GHL | Urgency DMs to all warm leads (15-20/day) | First WhatsApp voice notes to HOT leads | LinkedIn urgency post | Offer revealed across all channels | Not Started
2026-05-05 | Tuesday | 5 | Desire | Monitor Email 4 performance | DMs (15/day) — respond to all replies FAST | WhatsApp follow-ups (5-10/day) | Facebook group — share testimonial post | Responses tracked | Not Started
2026-05-06 | Wednesday | 5 | Desire | Launch Email 5 (Bonus Stack) | DMs (15/day) — highlight bonuses expiring | WhatsApp voice notes to new warm leads | LinkedIn post about results | Bonus urgency live | Not Started
2026-05-07 | Thursday | 5 | Desire | Monitor Email 5, prep Email 6 | DMs (10/day) — personal touch messages | WhatsApp follow-ups | Facebook group engagement | Desire building | Not Started
2026-05-08 | Friday | 5 | Desire | Launch Email 6 (Testimonials) | DMs (10/day) — share social proof | WEEKLY REVIEW: sales count, conversion rate | Prep Phase 4 (close) materials | Phase 4 prep started | Not Started
2026-05-09 | Saturday | 5 | Desire | Count sales so far. If < 10, extend deadline by 5 days | Final WhatsApp push to undecided leads | Review what's working, double down | Rest | Sales assessment | Not Started
2026-05-10 | Sunday | 5 | Desire | Plan close week (Phase 4) | Prep all final emails and DMs | Organize non-buyer list for re-engagement | Rest | Close week ready | Not Started
2026-05-11 | Monday | 6 | Action | Launch Email 7 (48hr Warning) | DM re-engagement of ALL non-buyers | WhatsApp final reminders to warm leads | LinkedIn final post | 48hr countdown started | Not Started
2026-05-12 | Tuesday | 6 | Action | Launch Email 8 (24hr Warning) | DMs (10/day) — personal last-chance messages | WhatsApp text messages with link | Monitor real-time sales | 24hr countdown | Not Started
2026-05-13 | Wednesday | 6 | Action | Launch Email 9 (Final Close — 6hrs before) | Last round of DMs to fence-sitters | WhatsApp final voice notes | CLOSE THE WINDOW — remove discount | CAMPAIGN CLOSED | Not Started
2026-05-14 | Thursday | 6 | Action | Send thank-you message to all buyers | Document final metrics across all channels | Calculate ROI and channel performance | Begin post-campaign analysis | Final metrics documented | Not Started
2026-05-15 | Friday | 6 | Action | Complete campaign post-mortem | Update Channel Performance sheet | Identify top-performing channels for next campaign | Plan next steps / repeat campaign | Campaign complete | Not Started
2026-05-16 | Saturday | 6 | Action | Rest + celebrate results |  |  |  |  | Not Started
2026-05-17 | Sunday | 6 | Action | [5 empty] | Not Started